## Checklist
Salmon Bake | 2021-07-03
| Assigned to | Due | Complete | Notes
Overall | Jeanne, Bob
Determine hours |  |  | done | noon - 3pm
Establish monthly status meetings | Jeanne
Get Health Department permit | Larry G
Assign Team Leaders | Jeanne
Health Dept & Permit | Larry Grambling |  | done
Purchasing - Food & Supplies | Phill Lutz |  | done
Purchasing - Salmon | Dick Throm |  | done
Purchasing - Ribs | Rick W
Cooking - Ribs | Rick W
Cooking - Salmon | Jerry Simonsen
Publicity | Penne Wilson |  | done
Tickets | Penne Wilson
Tickets - online | Bob Bedoll
Silent Auction | Peggy Hodge
Photo Contest | Val Oppenheim
Training Dinner | Carol Pascal
Physical Layout & Setup | Wayne Wallace
After-Sale | Paul Oppenheim
Parking | Nancy F
Music | ?
Dumpsters | Jeanne
Crew Lunch | Jeanne
Publicity
Sounder Article | Penne W | done | done
Newsletter article | Penne W | done | done
Post at store | Penne W
Post on Facebook | Penne W
Poster? If so, where post | Penne W
Sandwich Boards week before
AI Assistant | Bob | done | done
DAY BEFORE
Training Dinner Setup | Wayne Wallace |  |  | Tables & tents for 50. Single serving line in SB Shed.
Training Dinner Preparation | Carol Pascal
Training Dinner Servers | Carol Pascal, …
Training Dinner Food Handling Training | Dave Jacobsen, Larry Gambling
Training Dinner cleanup | Wayne Wallace
Setup Photo Contest | Val Oppenheim
Setup Silent Auction in AB | Peggy, Jon
Physical Setup | Wayne
Determine locations of events, special tables, parking | Wayne
Update map
Setup Decorations (?)
Put up tents, tables, chairs | Wayne |  |  | Tents for Tickets, and to cover tables in front of Farmhouse, and to cover desserts & hotdogs
Sound system set-up | Ed
Contact other volunteers
DAY OF --------------------------------
Non-Food
Put up tents, tables, chairs | Wayne |  |  | Tents for Tickets, and to cover tables in front of Farmhouse, and to cover desserts & hotdogs
Setup plates, silverware, tablecloths | Barbie Stockstad
Wood for Salmon bake | Todd
Salmon Bake pit setup | Jerry Simonsen
Setup for Hot Dogs
Credit Card (Square terminals) | Bob Bedoll
Cash Boxes for bake sale & cider & hotdogs | Todd | Sat 9/30
Ticket Sales | Dave Durette, Bob Bedoll
Lists of online ticket sales | Bob Bedoll
Prep & Setup
Salmon Cooking | Jerry S
Ribs | Rick W
Corn | Paul Oppenheim
Beans | Bill Hodge
Cole Slaw | Jane Groppenberger
Hot Dogs | Karen S, Cheryl Laschke
Drinks | Karen S
Dessert (Strawberry shortcake) | Karen S
Bread | Cherie D
Durring
Garbage | Young Life
Servers & Runners | Lora B
Food Safety | Larry Gambling
Lunch for Crew | Liane, Jane G?
AFTER
After sales | Paul Oppenheim
Dishwashing | Belin and David Schneider
Lessons Learned Dinner | Jeanne. |  |  | Pot luck.